## Sheet1
Instances
plugin | 2017 delivery | System wide | Description | Risk | Mitigation | Effort | Link
Course Contents | 70 courses | 439 courses | Provides an alternative course navigation, as a block | High | Develop a comms strategy on this plugin. It shoud be unnecessary, as it duplicates the functionality of existing navigation | Medium | https://gotafe.trainingvc.com.au/course/search.php?blocklist=55
Jaspersoft | N/A | N/A | Site wide, custom reporting. | High | eWorks are exploring alternatives, on befalf of all providers. | High | N/A
Select missing words question type | 271 qestions, across 64 courses | 1189 questions, across 257 courses | A question type that creates gap fill execrises. | Medium | Request plugin, via eWorks. No additional cost | Low | https://gotafe.trainingvc.com.au/report/questioninstances/?qtype=gapselect
Dialogue | 43 courses | 192 courses | Private discussions, within a course. Used largely in Animal Studies | Medium | Work with department to identify alternatives | Medium | https://gotafe.trainingvc.com.au/course/search.php?modulelist=dialogue&perpage=all
Group self selection (group choice) | 6 courses | 14 courses | Allows students to create an self enrol into groups | Medium | Work wiith staff to identify how they use this tool and plan for an alternative | Medium | https://gotafe.trainingvc.com.au/course/search.php?modulelist=groupselect
WebSMS | 7 courses | 46 courses | Ability to send SMS messages to students, from within a course | Medium | Work wiith staff to identify how they use this tool and plan for an alternative | Medium | https://gotafe.trainingvc.com.au/course/search.php?blocklist=54
OU Blogs | None | 48 courses | Blog tool, that can also be used for private journals | None | ? Disable plugin, to prevent accidental use between now and migration | Low | https://gotafe.trainingvc.com.au/course/search.php?modulelist=oublog
OU Wiki | None (in 3 ID17 courses) | 10 courses | Alternative to the inbuilt (core) wiki tool. | None | ? Disable plugin, to prevent accidental use between now and migration | Low | https://gotafe.trainingvc.com.au/course/search.php?modulelist=ouwiki
Clickview | Non, not used | Non, not used | Integrates Clickview into the content editor | None | None. Not used | None | N/A
Course overview on campus | Non, not used | Non, not used | An alternative display for the My Courses screen | None | None. Not used | None | N/A
OU edit dates | Non, not used | Non, not used | A mechansim to rapidly edit all dates in a course | None | None. Not used | None | N/A
Configurable reports | N/A. Not applied at the course level | Available to admins only | A method to run custom SQL reports on the live Moodle system | None | Replaced by MoodlRooms custom reports | None | N/A
Tile format | None | 3 courses | Androgic developed Course format (layout) | None |  | None | N/A